## Sheet1 (2)
Test Plan Documentation
Fields | Description
Project Name | Planetary_Pixels_076
Doc Version | 1.0
Date | 2024-11-15
Prepared By | Nazish Jehangir
Objective | The test plan aims to cover the scope, approaches, resources and schedule for the BBC website testing. It aims to ensure that the website meets the functional and usability standards and provides the best user experience.
Scope | To be tested: overall functionality and usability (e.g. navigation links, search features, image/video playback, sign-in and registration features.) Not to be tested: third-party services or marketing emails.
Test Approach | The testing approach aims to ensure a systematic testing of the website’s functionality and usability. the test methodology apart from user feedback will be including a combined manual testing and automated testing.
Resources Planning | Human Resources: a team lead, 2 manual testers, an automation & security engineer and an API tester. Test Tool: 1. Selenium: for automaion testing 2. Postman: for API testing 3. Jira: for defect/bug tracking and management 4. Zap: for security testing
Schedule | Phase 1: Funtional Testing - Start Date: 15/11/2024 ¦ End Date: 22/11/2024 Phase 2: Usability Testing - Start Date: 23/11/2024 ¦ End Date: 30/11/2024 Phase 3: Performance & Security Test - StartDate: 30/11/2024 ¦ End: 7/12/2024 Phase 4: Finally Regression Tesing - Start Date: 7/12/2024 ¦ End Date: 14/12/2024
Testing Phases | 1. Functional Testing 2. Usability Testing 3. Prformance & Security Testing 4. Regression Testing
Deliverables | test cases, defect reports, test execution reports, feedback and final validation.